## Burndown Chart
	Burn down chart

		Burned down		Balance		Daily Completed
	Days	Planned	Actual	Planned	Actual
	0			124	124	#N/A
	1	5	5	119	119	1
	2	48	52	71	67	6
	3	18		53	#N/A	#N/A
	4	21		32	#N/A	#N/A
	5	8		24	#N/A	#N/A
	6	0		24	#N/A	#N/A

sub-title