## Burndown Chart
	Burn down chart

		Burned down		Balance		Daily Completed
	Days	Planned	Actual	Planned	Actual
	0			53	53	#N/A
	1	24	14	29	39	2
	2	21	14	8	25	14
	3	8	25	0	0	25

sub-title